## Risk assessment 2021
|  | IDENTIFIED RISK | ACTION TAKEN/REQUIRED | 2021
UPDATE
Civic Centre and Civic Hall
1. | Roof of Civic Hall | Hall unusable, claims for loss of income | Reroofing approved by Council Feb 16. | -
2. | Accidents at Civic Hall | Claims, litigation | Inspection, insurance. | -
3. | Civic Group struggle or collapse | Loss of income | Maintain strong, firm relationship | Rent paid up to 31st December 2020. Continue to monitor in light of Covid-19.
|  | Empty building - vandalism etc. | Secure the building until re-let
4. | Rear of Civic Hall | Failure to let - vandalism, loss of income | Unit is vacant at present. | Space is being advertised. Toilet fitted.
5. | Incubator unit offices | Local economy weakens so income falls | Contract in place for management of units | Continue to monitor in light of Covid-19. Two tenants given notice to leave end January 2021.
|  | Problem tenants (not yet arisen) | Contract in place for management of units
|  | Car parking disputes | Pay for more spaces when needed
6. | Lease with WCC not yet signed | WCC increase service charge | Chase solicitors to finalise lease | Under discussion
|  | WCC create difficulties in relation to tenancy | Chase solicitors to finalise lease
7. | Civic Centre furniture and office equipment | Fire | Computer data save | -
|  | Data Loss | Repair & Renewal Fund
Insurance
Appliance Testing
Maintenance Contract/Self Insurance
Security Software
Contingency Planning
Annual Health & safety inspection
Town Council staff, administration and governance
8. | Staff | Loss of key staff especially if at same time | Periods of notice | New staff
|  |  | Business continuity plans | have contracts
9. | Governance and business procedures minimal | Exposure to financial loss and claims | Secure Council approval of procedures | -
10. | Responsibility for Health and Safety | Accidents to staff and/or service users, exposure to claims and financial loss and reputational damage | New Health & Safety Contract taken out with Ellis Whittam. Draft policy to be signed off and inspection to take place, initially on 11/1/21 but due to lockdown, this has been put on hold. | Town Clerk in contact with Health & Safety Company.
11. | Land and property registration and database | Claims, disputes, admin costs etc.. | Establish registration and database. Town Clerk working with WFDC. | Actively being progressed.
12. | Elected members | Insufficient future quantity and/or quality | Initiatives to encourage public interest. | Website and facebook page constantly updated when required.
Town Council finances
13. | Unexpected costs or sudden fall in income | Unplanned cuts to services during financial year | The council budgets carefully each year and maintains a minimum balance of £50,000 and other funds for specific purposes. | 2021/22 budget report draws members attention to the issue.
Abberley Avenue
14. | Public Open Space (Common Land) | Management & Maintenance | Grass cutting in growing season | -
Areley Kings
15. | Recreation Ground | Management and maintenance | Removal of fly tipped waste | -
|  |  | Insurance | -
|  |  | Annual Health & safety inspection | -
|  |  | Play Equipment installed | -
Allotment Land
16. | Kingsway | Management & maintenance of sites | Allotment Rep at each location | New rep.
17. | Areley Kings | Damage to site, loss of income, non-compliance with rules etc.. | Insurance. Attendance by our Parks Manager at allotment committee meeting. | required at Areley Kings.
Cemetery , Minster Road
18. | Land | Vandalism, Management & Maintenance | Annual Health & safety inspection, on site staffing, frequent inspections by Cemetery Supt. | -
19. | Cemetery Portakabin | Damage, Fire and Safety of staff and visitors | Insurance. Shipping Container was purchased in 2017. Hazardous substances now stored at Memorial Park. | Need to look at replacing, possibly with smaller one.
20. | Cemetery Toilet Block | Damage, Fire and Safety of staff and visitors | Appliance Testing | -
21. | Cemetery Office Contents | Damage, Fire, theft and Medical Pandemic | Contingency Planning | -
|  |  | Computerising of cemetery records ongoing. | -
Vale Road/ Mitton Street
22. | Public Gardens | Management & Maintenance and Vandalism | Insurance | -
Memorial Park |  |  | Arboricultural survey | -
23. | Stourport Com Centre - Changing Rooms, Building | Damage, Fire and Safety of staff and visitors | Arboricultural 2 year remedial work | -
24. | Stourport Com Centre - Changing Rooms, Contents | Damage Fire and theft | Grass cutting in growing season | -
25. | Memorial Park Bandstand | Materials Damage | Daily visit by staff | -
|  |  | Improvements to bandstand were made in 2018 and more are being looked into. | -
26. | War Memorial Gates, Railings and Play Equipment | Damage and theft | Contingency Planning | -
|  |  | Annual Health & safety inspection | -
|  |  | Green Gym, Play Areas | -
27. | Trees within Memorial Park and other sites | Damage and falls, safety of general public. | Tree inspection and Management SLA with Wyre Forest District Council | Agreement in place. Ongoing works scheduled.
Town Clock and Clock Tower
28. | Town Clock and Tower | Management & Maintenance | Weekly inspection | Ongoing
|  |  | Insurance | -
|  |  | Structural Engineer Inspections | -
Bus Shelters and Public Seats
29. | Bus Shelters and Public Seats | Management & Maintenance | Insurance | -
|  | Vandalism | Inspection | -
|  |  | Staff patrols | -
Street Lighting
30. | Street Lighting | Management & Maintenance | Insurance | -
|  | Vandalism | Inspection | -
|  |  | Staff patrols | -
Christmas Lights
31. | Christmas Lights | Management & Maintenance | Insurance | Christmas lights
|  |  | Staff & Volunteer Training | are stored in a
|  |  | Health & safety inspection | portakabin at the
|  |  | Risk Assessment | cemetery.
32. | Vehicles and Plant
| General Purpose Van | Management & Maintenance | Insurance | -
| John Deere Mini Tractor | Vandalism, Theft | Servicing & testing | -
| John Deere Pedestrian Mower | Theft | Repair & Renewal Fund | -
| Ride on Mower | Theft | Repair & Renewal Fund | -
33. | Civic Items
| Mayor's Robe Chain and Badge | Theft | Insurance | -
| Coat of Arms and Silver Casket | Damage | Security | -
| Display Case, Chest and Contents | Theft | Insurance | -
Contracts
34. | Contracts | Management | Risk Register | -
|  | Liquidation/Bankrupcy | Contingency Planning | -
|  |  | Engagement of specialists | -
|  |  | Council Standing Orders | -
|  |  | Financial Regulations | -
|  |  | Minimise no. of contracts entered into | -